## Sayfa1
|  |  |  | SPRINT ONE | [14 empty] | SPRINT TWO | [14 empty] | SPRINT TREE | [14 empty] | SPRINT FOUR
Activity Number | Task Summary | Assignee | Duration | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project kickoff, team roles & communication plan | Emir, Aylin | 1 | bar: Week 1 M to Week 1 F
2 | Requirement gathering, user stories & privacy checklist | Kerem, Yağmur | 1 | bar: Week 2 M to Week 3 F
3 | System architecture & data model design | Emir, Kerem | 2 | bar: Week 4 M to Week 6 F
4 | Wireframes, UI style guide & design system | Aylin, Yağmur | 2 | bar: Week 4 M to Week 5 F
5 | Clickable prototype & usability testing | Aylin, Yağmur | 1 | bar: Week 6 M to Week 6 F
6 | Core backend development (auth, user profile, data model) | Emir, Kerem | 3 | bar: Week 7 M to Week 9 F
7 | Event creation & availability features | Aylin, Yağmur | 2 | bar: Week 8 M to Week 9 F
8 | System and Integration Testing | Yağmur,Aylin | 2 | bar: Week 9 M to Week 10 F
9 | User Acceptance Testing (UAT) & Defect Resolution | Emir, Aylin | 2 | bar: Week 9 R to Week 11 W
10 | Bug fixing | All Team | 2 | bar: Week 10 M to Week 11 F
11 | Final presentation, deployment | All Team | 2 | bar: Week 10 F to Week 12 R
12 | project documentation | All Team | 1 | bar: Week 12 M to Week 12 F